# Limberlost HOA Portal

8-Week Implementation Schedule (May 18 — July 6, 2026)

# 1. Schedule at a Glance

Build window: 8 weeks. Buffer week is Week 7 to absorb any slippage; launch target is the first week of July 2026.

| Week | Dates | Focus | Exit Criteria |
| --- | --- | --- | --- |
| 1 | May 18 – May 24 | Foundation: accounts, repo, scaffold | GitHub repo live, Cloudflare Pages auto-deploys on push, Supabase project created |
| 2 | May 25 – May 31 | Public surface | Homepage and Contact page live at preview URL with placeholder content |
| 3 | Jun 1 – Jun 7 | Headless CMS integration | Decap CMS at /admin, admin can post a test event end-to-end |
| 4 | Jun 8 – Jun 14 | Auth + Owner Dashboard shell | Magic-link login works, dashboard tabs render with mock data |
| 5 | Jun 15 – Jun 21 | Dues + Admin tools | Admin dues table reads/writes Supabase; owner sees correct status |
| 6 | Jun 22 – Jun 28 | Mass email + content seeding | Admin sends test email to Jose + admin via Resend; real content imported |
| 7 | Jun 29 – Jul 5 | QA, accessibility, training | WCAG AA pass, admin completes runbook walkthrough with Jose |
| 8 | Jul 6 – Jul 12 | Launch | Porkbun DNS cutover, owners onboarded, monitoring in place |

# 2. Week-by-Week Detail

## Week 1 — Foundation (May 18 – May 24)

- Create GitHub org ‘limberlost-hoa’ and repo ‘portal’; commit Next.js scaffold from this build session.

- Create Cloudflare account, connect Pages to the GitHub repo, enable auto-deploy on push to main.

- Create Supabase project; run the schema DDL from Doc 2; seed two test owner rows.

- Create Resend account; verify the sending domain (TXT record at Porkbun).

- Document every account login in a password manager (e.g. Bitwarden) handed to the admin.

Risk: domain DNS propagation can take up to 24 hours — start the Porkbun + Resend DNS records on Day 1.

## Week 2 — Public Surface (May 25 – May 31)

- Build / (homepage) with hero image, welcome paragraph, big “Owner Login” button.

- Build /contact with board email and physical address.

- Implement the design system: typography, color tokens, button component, focus rings.

- Add favicon, manifest, Open Graph tags.

Risk: hero image asset blocking timeline — use a placeholder, swap before launch.

## Week 3 — CMS Integration (Jun 1 – Jun 7)

- Add Decap CMS at /admin: config.yml, OAuth via GitHub.

- Wire homepage, contact page, events, members, and HOA docs to read from /content/.

- Test that an admin commit triggers a Cloudflare rebuild in under 60 seconds.

Risk: Decap GitHub OAuth setup requires a Netlify account as the OAuth proxy (free) — plan for one extra hour.

## Week 4 — Auth + Dashboard Shell (Jun 8 – Jun 14)

- Implement Supabase Auth magic-link flow: /login page + /auth/callback handler.

- Build /portal layout: 4 tabs (Documents, Events, Members, My Dues).

- Mock data for dues so visual design is reviewable before wiring to Supabase.

- Customize the Supabase magic-link email template with the copy in Doc 3.

## Week 5 — Dues + Admin (Jun 15 – Jun 21)

- /portal/dues reads dues for the signed-in owner only (RLS-gated).

- /admin/dues table: 45 rows, status dropdown, save inline, audit who-changed-what.

- Add storage bucket for hoa-pdfs and wire /portal/documents to list signed URLs.

## Week 6 — Mass Email + Content (Jun 22 – Jun 28)

- /admin/email: subject + body (Markdown) + preview + Send button.

- Send goes through a Cloudflare Pages function (or Supabase Edge Function) that calls Resend.

- Audit log: every send recorded in announcements table.

- Import real HOA documents (rules, bylaws, current meeting minutes) and current board member bios.

## Week 7 — QA & Training (Jun 29 – Jul 5)

- Full accessibility audit: VoiceOver, NVDA, keyboard-only, 200% zoom.

- Cross-browser test: Safari (iOS + macOS), Chrome (Android + Windows), Edge.

- Performance: Lighthouse score 95+ on every public page.

- Hand the runbook (Doc 5) to the admin; do a recorded screen-share walkthrough.

- Buffer day for last-minute fixes.

## Week 8 — Launch (Jul 6 – Jul 12)

- Day 1 (Mon): Porkbun DNS → update nameservers to Cloudflare. Wait for propagation.

- Day 2 (Tue): point limberlosthoa.com at Cloudflare Pages. Verify SSL provisioned.

- Day 3 (Wed): seed real owners table (all 45) via SQL import.

- Day 4 (Thu): admin sends invite emails to all 45 owners (Supabase dashboard → Invite User).

- Day 5 (Fri): monitor sign-ins, field support questions, send a launch announcement.

# 3. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| DNS propagation slips | Medium | Low | Cut over on a Monday; admin keeps printed handout for owners during the cutover day. |
| Owner emails bounce | Medium | Medium | Admin verifies all 45 emails with each owner by phone before send. |
| Resend domain not verified | Low | High | Verify the Porkbun TXT records in Week 1; do not wait until launch. |
| Decap GitHub OAuth misconfigured | Medium | Medium | Walk through Decap docs in Week 3; budget one full day. |
| Admin uncomfortable with CMS | Medium | High | Week 7 hands-on training + printed runbook + screen recording. |
| Supabase free-tier outage | Low | Medium | Public pages stay up regardless; communicate to owners via email if it happens. |

# 4. Definition of Done (Launch Gate)

- All 45 owners have received an invite email and at least 80% have signed in successfully.

- Admin has independently posted one event, uploaded one PDF, toggled one dues row, and sent one mass email — without Jose touching the keyboard.

- Lighthouse: Performance ≥ 95, Accessibility = 100, Best Practices ≥ 95, SEO ≥ 90 on every public page.

- WCAG 2.2 AA audit complete with zero critical issues.

- Backup tested: Supabase daily backups verified by restoring to a sandbox project.